## Introduction
OLIS GAP ANALYSIS QUESTIONNAIRE
(2013-02-07) External
Purpose
The purpose of this gap analysis questionnaire is to gather key information about an adopter organization’s processes and systems to determine the gaps that will need to be addressed in order for the organization to successfully develop and support an LIS-to-OLIS interface.
Audience
This document should be completed by the adopter project manager with input from resources in the following areas: clinical, system development, network, privacy and security, legal.
Instructions
Completion of the questionnaires is often an iterative process, and the OLIS initiative lead/CPIS will schedule regular meetings (teleconferences) to ensure that the contents are fully understood by the organization and finalized as soon as possible. The CPIS can provide feedback and advice on the implications of alternative approaches to addressing gaps. Note: It is strongly recommended that the vendor(s) be included in these meetings, where appropriate. This can reduce confusion and miscommunication later on in the project when system requirements are developed.
Before each meeting, the adopter project manager should provide the initiative lead/CPIS with the latest iteration of the questionnaires, as required. However, once all the questions have been answered and finalized, the adopter should summarize their unique issues (e.g., LIS, other systems, processes, specification, technical) and email the finalized version of the documents to the CPIS.
Reference Documents
When completing this gap analysis questionnaire, the following documents may be referenced (and accessed from the OLIS collaboration portal):
· OLIS Interface Specifications
· A Guide to the OLIS Nomenclatures
· OLIS Conformance Test Scenarios
· The Adopter’s Guide to Implementing OLIS

## Issues
Gap Analysis Issues Summary
Note: This section should be completed as issues are identified. Upon completion of gap analysis and pre-CT analysis, this section should contain a summary of all identified issues.
Item # | Status | Issue Type | Issue | Date Logged | Priority | Issue Owner | Reference | Details | Investigation / Solution
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37

## Index
Index
A |  | Environment, test | BUS-60 | N |  | Reportable results | GEN-19 | Titres, cold agglutinin screen | BLO-07
ABO results | BLO-02, 03 | Environment, test, LIS release | BUS-62 | Narrative text | PAT-02, PAT-04, | Reporting, corrections | MIC-06 | Topology/schema, network | BUS-31
Access to results outside org | BUS-19 | Environment, test, modifications/upgrades | BUS-62 |  | BLO-06, 07, 08, 09, | Reporting, manual differential | HEM-05 | TRA | BUS-33
Access to results, providers | BUS-57 | Envrionment, test, maintenance | BUS-61 |  | 10, 12 | Reporting, organisms/sensitivities | MIC-02 | TRA, org expertise | BUS-34
Accession numbers, format | GEN-05 | Extract, test dictionary | BUS-37 | Network services, orgs/vendors | BUS-31 | Reporting, partial | BUS-56 | Transfusion reactions, investigations | BLO-12
Accession numbers, maximum characters | GEN-05 | F |  | Network, ONE network | BUS-20 | Reporting, PT/INR | HEM-06 | Transmit to OLIS, system | BUS-53, GEN-13
Accession numbers, multiple orders | GEN-07 | Family study | PAT-09, BLO-11 | Network, topology/schema | BUS-31 | Required, work to meet spec | BUS-69, 70 | Type (blood bank) | BLO-03
Accession numbers, order numbers | GEN-07 | Fetal maternal bleed | BLO-08 | Non-insured (private pay) tests | GEN-09 | Resources, OLIS expertise | BUS-78 | U
Accession numbers, reuse | GEN-05 | File formats, pathology | PAT-05 | O |  | Resources, project team | BUS-80 | Undifferentialed lines of text, OBX.3 | GEN-12
Addenda, final reports, pathology | PAT-05 | Format, interface | BUS-54 | OBX.3, test codes | GEN-12 | Resources, registration | BUS-59 | Upgrades, IT/lab | BUS-72
Agreements, eHealth Ontario | BUS-22 | Formats, file, pathology | PAT-05 | ONE network | BUS-20 | Resources, work together | BUS-79 | Upgrades, IT/lab and OLIS timelines | BUS-73
Agreements, approval process/timelines | BUS-71 | Frozen sections | PAT-03 | ONE network, bandwidth | BUS-27 | Results, ABO | BLO-02, 03 | V
Alliances, business | BUS-1 | G |  | ONE network, bandwidth, shared | BUS-28 | Results, antibody investigation | BLO-04 | Version code, health card | BUS-42
Ancilliary information | GEN-16 | Genetic test reports | PAT-08 | ONE network, technical support | BUS-25 | Results, antibody screen | BLO-03 | View results online | BUS-18
Antibody investigation | BLO-04 | Go-live filter (throttle) | BUS-15 | Online results viewing | BUS-18 | Results, antibody titres | BLO-05 | Volume, annual lab tests | BUS-29
Antibody screen | BLO-03 | Governance structure | BUS-2 | Operating system | BUS-67 | Results, cold agglutinin screen | BLO-07 | Volume, seasonal variability | BUS-30
Antibody titres | BLO-05 | Group (blood bank) | BLO-03 | Order entry system, electronic | BUS-16 | Results, cold agglutinin screen, titres | BLO-07 | Volume, tests by modality | BUS-36
Antigen typing results | PAT-09, BLO-11 | Guidelines, align with project | BUS-77 | Order method, LIS | GEN-04 | Results, correction | GEN-14 | W
Approval process, agreements | BUS-71 | H |  | Order, cancellation | GEN-11 | Results, culture | MIC-02 | Web access, workstations | BUS-66
Automated differential | HEM-01 | Hams test | BLO-10 | Order, modifications | GEN-10 | Results, direct antiglobulin | BLO-06 | Web browser | BUS-67
B |  | Health card number, ORU message | BUS-43 | Orders, blood bank | BLO-01 | Results, Donath Landsteiner | BLO-09 | Work required to meet spec | BUS-69, 70
Bandwidth | BUS-26 | Health card number, version code | BUS-42 | Orders, HL7 interface | BUS-17 | Results, fetal maternal bleed | BLO-08 | Workstations, web access | BUS-66
Bandwith, shared | BUS-28 | Health card numbers | BUS-41 | Org expertise, OLIS resources | BUS-78 | Results, group (blood bank) | BLO-03
Blocking indicators | BUS-51 | Help desk structure/process | BUS-58 | Org expertise, PIA | BUS-34 | Results, Hams test | BLO-10
Browser, web | BUS-67 | HISs | BUS-10 | Org expertise, TRA | BUS-34 | Results, invalidation | GEN-15
Business alliances | BUS-1 | HL7 interface, orders | BUS-17 | Organisms, corrections | MIC-04 | Results, move to another patient | BUS-48
Business alliances, related initiatives | BUS-4 | HL7 interfaces | BUS-11 | Organisms, parent-child relationship to sensitivities | MIC-02 | Results, preliminary | BUS-55
Business alliances, work together | BUS-3 | HL7 interfaces, purposes | BUS-12 | P |  | Results, Rh | BLO-02, 03
Business processes | GEN-03 | I |  | Parent-child relationship, organisms/sensitivities | MIC-02 | Results, type (blood bank) | BLO-03
C |  | Images, genetic test reports | PAT-08 | Parent-child relationship, pathology specimens | PAT-04 | Reuse accession numbers | GEN-05
Cancellations, order | GEN-11 | Images, pathology | PAT-05 | Partial reports | BUS-56 | Rh results | BLO-02, 03
Cancellations, test | GEN-11 | Impact, internal processes | BUS-76 | Paternity investigation | PAT-09, BLO-11 | Risks | BUS-75
Cancer Care Ontario | GEN-19, PAT-01, 02 | Impact, planned events, projects | BUS-74 | Patient demographics, list | BUS-47 | S
CBC, automated differential | HEM-01 | INR | HEM-06 | Patient demographics, modified | BUS-46 | Seasonal variability, volume | BUS-30
Chemistry, serology | CHE-01 | Insured tests | GEN-09 | Patient identifiers, assign/select | BUS-44 | Security | BUS-33
Clinical disciplines | BUS-35 | Interface engines | BUS-9 | Patient identifiers, merge | BUS-49 | Sensitivities, method | MIC-04
Clinical trials | GEN-03 | Interface format | BUS-54 | Patient identifiers, reused | BUS-45 | Sensitivities, parent-child relationship to orgs | MIC-02
Cold agglutinin screen | BLO-07 | Interfaces, diagram | BUS-13 | Patient records, split | BUS-50 | Serology, chemistry | CHE-01
Cold agglutinin screen, titres | BLO-07 | Internal processes, impact | BUS-76 | Patient, health numbers | BUS-41 | Serology, chemistry, microbiology | CHE-01, MIC-09
Collector's comments | GEN-16 | Interpretation comments | GEN-17 | PIA | BUS-33 | Serology, microbiology | MIC-09
Colony counts | MIC-05 | Invalidations, pathology | PAT-07 | PIA, org expertise | BUS-34 | Services, eHealth Ontario | BUS-23
Comments | GEN-16 | Invalidations, test result | GEN-15 | PIMS | PAT-01, 02 | Sort keys | GEN-02
Configuration, desktop | BUS-68 | Invalidations, test result, microbiology | MIC-07 | PKI certificates | BUS-64, 65 | Specimens, multiple, microbiology | MIC-01
Connectivity path | BUS-25 | Investigations, transfusion reactions | BLO-12 | Planned events, projects, impact | BUS-74 | Specimens, multiple, pathology | PAT-04
Consent directives | BUS-51 | IT/lab upgrades | BUS-72 | Policies, align with project | BUS-77 | Specimens, receive | BUS-52, GEN-04
Constraints | BUS-75 | IT/lab upgrades, OLIS timelines | BUS-73 | Practitioner, demographics | GEN-01 | Specimens, type | GEN-20
Corrections, organisms, microbiology | MIC-06 | L |  | Preliminary results, frozen sections | PAT-03 | Split, patient records | BUS-50
Corrections, pathology | PAT-06 | LIS, order method | GEN-04 | Preliminary results, general | BUS-55 | Standards, align with project | BUS-77
Corrections, test result | GEN-14 | LISs | BUS-8 | Privacy | BUS-33 | Support, systems | BUS-14
Culture results | MIC-02 | Local registration authorities | BUS-24 | Private pay tests | GEN-09 | System, transmit to OLIS | BUS-53, GEN-13
D |  | LOINC | BUS-40 | Processes, business | GEN-03 | Systems support | BUS-14
Data cleansing | BUS-63 | LRAs | BUS-24 | Processes, internal, impact | BUS-76 | T
Data type, results | GEN-21 | M |  | Project team | BUS-80 | Technical support, ONE network | BUS-25
Date/time stamps | GEN-06 | Manual differential | HEM-02 | Providers, access to results | BUS-57 | Test codes, impact on other orgs | BUS-39
Demographics, patient | BUS-47 | Manual differential, reflex | HEM-03 | PT | HEM-06 | Test codes, OBX.3 | GEN-12
Demographics, practitioner | GEN-01 | Manual differential, reflex, order ID | HEM-04 | PT/INR, reporting | HEM-06 | Test codes, used by other orgs | BUS-38
Dependencies | BUS-75 | Manual differential, reporting | HEM-05 | Public health lab | GEN-03,19, MIC-08 | Test dictionary, extract | BUS-37
Desktop configuration | BUS-68 | Mapping codes, impact on other orgs | BUS-39 | R |  | Test environment | BUS-60
Diagram, interfaces | BUS-13 | Merge, patient identifiers | BUS-50 | Receive specimens | BUS-52 | Test environment, LIS release | BUS-62
Differential, automated | HEM-01 | Method, sensititivies | MIC-04 | Record-oriented/discrete format | BUS-54, GEN-12 | Test environment, modifications/upgrades | BUS-62
Differential, manual | HEM-02 | Microbiology, chemistry, serology | CHE-01 | Reference citations | GEN-17 | Test envrionment, maintenance | BUS-61
Differential, manual, reflex | HEM-03 | Microbiology, multiple specimens | MIC-01 | Reference ranges | GEN-17 | Test not performed | GEN-18
Differential, manual, reflex, order ID | HEM-04 | Microbiology, serology | MIC-09 | Referral consultant reports, pathology | PAT-05 | Test requests, multiple, single order | GEN-07
Differential, manual, reporting | HEM-05 | Modalities | BUS-35 | Referral in | BUS-5, GEN-22 | Tests not performed | GEN-03
Direct antiglobulin | BLO-06 | Modalities, test volume | BUS-36 | Referral out | BUS-6, GEN-23 | Tests, cancellations | GEN-11
Display-oriented format | BUS-54, GEN-12 | Modification, patient demographics | BUS-46 | Referrals, business processes | GEN-03 | Tests, reflex | GEN-08
Donath Landsteiner | BLO-09 | Modify order | GEN-10 | Referrals, future | BUS-7 | Therapeutic range | GEN-17
E |  | Multiple specimens, microbiology | MIC-01 | Reflex test | GEN-08 | Throttle (go-live filter) | BUS-15
eHealth Ontario agreements | BUS-22 | Multiple specimens, pathology | PAT-04 | Registration, resources | BUS-59 | Timelines, agreements | BUS-71
eHealth Ontario services | BUS-23 | Multiple test requests, single order | GEN-07 |  |  | Titres, antibody | BLO-05

## Overview
Overview
General Information
Organization Name:
Address (Main Site):
Site Names:
Functionality in Scope: | Results into OLIS | Results out of OLIS (clinical viewer) |  | Referrals out | Referrals in |  | Order retrieval (walk-ins) |  | eOrdering
Modalities in Scope: | Biochemistry | Hematology |  | Microbiology | Blood Bank |  | Pathology |  | Other (specify)
Contacts
Role | Contact Name |  | Title |  |  | Phone / Ext. |  | Email
Adopter Project Manager
LIS Application Specialist
IT Network Support
Registration Specialist
Lab Clinician, Biochemistry
Lab Clinician, Hematology
Lab, Clinician, Microbiology
Lab Clinician, Blood Bank
Lab Clinician, Pathology
Document Review History
Date | Participants

## Business
Business | [13 empty] | 4 columns | 3 columns | 2 columns | 2 columns (H+I) | 2 columns | 2 columns | 2 columns (J+K) | 2 columns (K+L) | 2 columns (M+N) | 3 columns (L+M+N) | 4 columns | 4 columns + K | 6 columns | Essay starting at D | Essay starting at E | Table starting at Column G | Essay starting at Column H | Essay starting at Column I | Essay starting at Column J | Essay starting at Column K | Essay starting at Column L | Essay starting at Column M | Essay starting at Column N | All columns (essay answer)
Tip: When you have finished typing in a cell, double-click on the cell to display all of the text. | [13 empty] | 62.84 | 47.13 | 31.42 | 31.42 | 31.42 | 31.42 | 42 | 42 | 29.57 | 45.28 |  |  | 94.26 | 181.54 | 165.83 | 134.41 | 118.7 | 102.99 | 87.28 | 71.57 | 45.28 | 29.57 | 15.14
Organization and Team Structure - Business Alliances
1. |  | Do you have business alliances with other organizations? If so, please list these organizations and provide detailed information on the nature of these relationships (e.g., governance structure).
|  | Organization |  |  |  | Nature of Relationship
[24 empty] | 0 | 0
[24 empty] | 0 | 0
[24 empty] | 0 | 0
2. |  | Describe your organization’s current governance structure pertaining to information systems. Does this governance structure also apply to your business alliance? If not, please explain the difference.
|  | <Enter> | [34 empty] | <Enter>
3. |  | Will your business alliances work together to implement OLIS? Please provide information on how your organizations will work together.
|  | <Enter> | [34 empty] | <Enter>
4. |  | Are there any related initiatives that you will need to integrate with or can leverage?
|  | <Enter> | [34 empty] | <Enter>
Organization and Team Structure - Referral Alliances
5. |  | Which health care organizations refer work to you? For each referral relationship, please describe your referral process (e.g., electronic vs paper-based referrals).
|  | Your Organization | Org Who Refers to Your Org | Clinical Discipline | # spec/ month | Mode (HL7, Paper, Req, Fax) | How are reports distributed? |  | Types of tests referred in? |  | Comments
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
6. |  | To which health care organizations do you refer work? For each referral relationship, please describe your referral process (e.g., electronic vs paper-based referrals).
|  | Your Organization | Org You Refer To | Clinical Discipline | # spec/ month | Mode (HL7, Paper, Req, Fax) | Results manually entered into LIS? |  | Original reports distributed? |  | Comments
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
[17 empty] | 0 |  |  | 0 |  |  | 0
7. |  | Please list any potential future electronic referral partners (in or out).
|  | Referral Partner Name |  | Refers Work to Our Lab | Refer Work to Their Lab
0
0
0
0
0
0
Information Technology - General
8. |  | Which laboratory information system(s) are currently implemented in your laboratory? Please identify all vendors and versions.
|  | Clinical Discipline |  | LIS Vendor |  | LIS Application Name |  | Version / Release | Approx. Date of Last Upgrade | Approx. Date of Next Upgrade | Comments
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
9. |  | Please provide details about your current interface engine(s) which transmit and/or filter and/or transform HL7 messages to/from your LIS.
|  | Clinical Discipline |  | Vendor |  | Application Name |  | Version / Release | Approx. Date of Last Upgrade | Approx. Date of Next Upgrade | Comments
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
[16 empty] | 0 | 0 | [5 empty] | 0
10. |  | What hospital information system(s) are currently implemented in your organization? Please identify all vendors and versions.
|  | HIS Vendor |  |  |  | HIS Application Name |  | Version / Release | Approx. Date of Last Upgrade | Approx. Date of Next Upgrade | Comments
[14 empty] | 0 |  |  | 0 | [5 empty] | 0
[14 empty] | 0 |  |  | 0 | [5 empty] | 0
[14 empty] | 0 |  |  | 0 | [5 empty] | 0
[14 empty] | 0 |  |  | 0 | [5 empty] | 0
[14 empty] | 0 |  |  | 0 | [5 empty] | 0
[14 empty] | 0 |  |  | 0 | [5 empty] | 0
[14 empty] | 0 |  |  | 0 | [5 empty] | 0
11. |  | Do you have any HL7 interfaces to/from any of your laboratory information system(s)?
If so, please describe below and provide a schematic including each of your HL7 interfaces. As well, please provide the electronic interface specification documentation as implemented for your organization (including any local customizations).
|  | Interface Name |  |  |  | Sending System |  | Receiving System |  | Schematic Attached? (Y/N) | Interface Spec Attached? (Y/N)
[14 empty] | 0 |  | 0 | 0 | [5 empty] | 0
[14 empty] | 0 |  | 0 | 0 | [5 empty] | 0
[14 empty] | 0 |  | 0 | 0 | [5 empty] | 0
[14 empty] | 0 |  | 0 | 0 | [5 empty] | 0
[14 empty] | 0 |  | 0 | 0 | [5 empty] | 0
[14 empty] | 0 |  | 0 | 0 | [5 empty] | 0
12. |  | For what purpose(s) are these interfaces being used (e.g., order entry, results to clinical repository/viewer)?
|  | Interface Name |  |  |  | Purpose
[14 empty] | 0 | [14 empty] | 0
[14 empty] | 0 | [14 empty] | 0
[14 empty] | 0 | [14 empty] | 0
[14 empty] | 0 | [14 empty] | 0
[14 empty] | 0 | [14 empty] | 0
[14 empty] | 0 | [14 empty] | 0
13. |  | Using a diagram and supporting text, identify and document your present LIS and the manual/electronic interfaces with laboratory partner organizations. | [9 empty] | Attached? | <Select>
(Include architectural diagrams and data flow diagrams – data flowing to/from the LIS to/from systems with your organization, and data flowing to/from the LIS to laboratory partner organizations.)
Note: Please label the nature of the data (Index/ADT, orders, results),
14. | a. | Are your information systems maintained and supported internally or externally? | [6 empty] | <Select> | [22 empty] | #REF!
| b. | If externally, by whom? |  | <Enter> | [23 empty] | <Enter>
15. |  | Does the system provide administrator controls that will allow the transmission of messages to OLIS to be delayed, and/or enabled and disabled for each lab test modality (i.e., to support a go-live filter/throttle)? | [10 empty] | <Select>
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
Information Technology - Electronic Order Entry System
16. |  | Does your staff use an electronic order entry system to order laboratory tests? | [6 empty] | <Select> | [21 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
17. |  | If YES, does the LIS receive the orders via an HL7 interface? | [6 empty] | <Select> | [21 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
Information Technology - Results Viewing
18. | a. | Does your staff view your laboratory’s orders and results online? | [6 empty] | <Select>
| b. | If YES, describe below how the results are viewed by clinical and laboratory users within and outside your organization.
|  | How are lab results viewed within your organization? | [5 empty] | How are lab results viewed outside your organization?
[26 empty] | 0 |  |  |  |  | 0
19. | a. | Does your staff have access to laboratory orders and results originating from outside your org? | [6 empty] | <Select> | [23 empty] | 0
| b. | If YES, please describe: |  | <Enter> | [23 empty] | <Enter>
Network Connectivity - eHealth Ontario Network Access
Note: Your OLIS initiative lead can provide assistance with answering some of the following questions.
20. |  | Is your organization currently connected to the eHealth Ontario ONE® Network (e.g., MPN or eWAN)? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
21. | a. | Are any of your organization’s sites connected to the eHealth Ontario ONE Network service through another org? | [6 empty] | <Select> | [24 empty] | 0
| b. | If YES, please identify the site(s) where the eHealth Ontario ONE Network service is installed. | [27 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
22. |  | Has your organization signed any of the following eHealth Ontario agreements?
|  | Agreement / Schedule |  | Date Signed (mm/dd/yy) |  | Agreement / Schedule |  | Date Signed (mm/dd/yy)
|  | Services Agreement |  |  |  | PKI Service Module | [9 empty] | 0 | 0
|  | ONE Network Agreement |  |  |  | PKI Service Schedule | [9 empty] | 0 | 0
|  | ONE ID Direct Service Module | [13 empty] | 0 | 0
23. |  | Which services that use connectivity to eHealth Ontario have been implemented? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
24. |  | Does your organization have one or more local registration authorities (LRAs) for eHealth Ontario services? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
25. |  | Explain the connectivity path from your organization to eHealth Ontario? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
26. |  | Who provides technical support for your connections to the eHealth Ontario network? Describe the nature of this support. | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
27. |  | What is the bandwidth for your eHealth Ontario network connection(s)? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
28. | a. | Is this bandwidth shared by external users (e.g., portal access to clinicians, shared network with other health care orgs)? | [6 empty] | <Select> | [24 empty] | 0
| b. | If YES, please describe: |  | <Enter> | [23 empty] | <Enter>
29. |  | Estimate your annual laboratory test volumes.
|  | Biochemistry: | <Enter> | Hematology: | <Enter> | Microbiology: | <Enter> | Blood Bank: | <Enter> | Pathology: | <Enter> | Other: | <Enter>
30. | a. | Is there any seasonal or diurnal variability in reporting patterns and volumes? | [6 empty] | <Select> | [21 empty] | 0
| b. | If YES, please describe: |  | <Enter> | [23 empty] | <Enter>
31. |  | Does your organization have business relationships with other organizations or vendors for providing network services? | [6 empty] | <Select>
If so, please identify these providers and outline the nature of their services
|  | Organization / Vendor Name |  |  |  | Nature of Services
[14 empty] | 0 | [16 empty] | 0
[14 empty] | 0 | [16 empty] | 0
[14 empty] | 0 | [16 empty] | 0
[14 empty] | 0 | [16 empty] | 0
[14 empty] | 0 | [16 empty] | 0
[14 empty] | 0 | [16 empty] | 0
32. |  | Do you have a network topology/schema? If so, please provide along with any explanatory notes. | [5 empty] | Attached? | <Select>
33. | a. | Please identify the name and physical location of the computer(s) which host the application that will sign outgoing messages.
<Enter>
| b. | Please identify the name and physical location of the computer(s) which host the application that will connect directly to OLIS.
<Enter>
Privacy and Security
34. |  | Has your organization previously completed PIAs and TRAs for data sharing arrangements? | [6 empty] | <Select> | [24 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
35. |  | Do you have the expertise/experience within your org to complete these documents with respect to implementing interface(s) to OLIS? | [6 empty] | <Select> | [24 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
Nomenclature Mapping
36. |  | For which clinical disciplines does your laboratory conduct tests? (e.g., chemistry, hematology, blood bank, pathology, microbiology, serology, immunology)
|  | Biochemistry: | <Select> | Hematology: | <Select> | Microbiology: | <Select> | Blood Bank: | <Select> | Pathology: | <Select> | Other: | <Select>
Specify:
37. |  | For each clinical discipline, how many different tests can be ordered and how many different tests can be reported?
|  | Biochemistry |  | Hematology |  | Microbiology |  | Blood Bank |  | Pathology |  | Other
|  | Ordered | Reported | Ordered | Reported | Ordered | Reported | Ordered | Reported | Ordered | Reported | Ordered | Reported
38. |  | Can you extract your complete test requests and test results dictionaries (including all metadata)? Do you require vendor participation/support or third party support for extracting these dictionaries as electronic files?
| a. | Extract dictionaries |  | <Select> | Comments: | <Enter> | [22 empty] | <Enter>
| b. | Vendor support |  | <Select> | Comments: | <Enter> | [22 empty] | <Enter>
39. |  | Are your order and result test codes used by any other organizations? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
40. |  | Would mapping your local codes to a provincial standard nomenclature have any impact on other org’s lab data? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
41. | a. | Does your LIS use logical observation identifiers names and codes (LOINC)? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| c. | If so, which organization is the source of this information (e.g., Regenstrief, Canada Health Infoway)? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
Operation Capability - Current State
42. | a. | Do you store the patient’s jurisdictional (e.g., Ontario) health number in the LIS? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| c. | If YES, how do you capture the health number? | [5 empty] | <Select> | [25 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| c. | If YES, where are they stored? | [5 empty] | <Select> | [25 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| d. | If LIS, are they: | [5 empty] | <Select> | [25 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| d. | If YES, do you always validate Ontario health cards? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| e. | If YES, do you capture and store the patient’s name, sex and DOB as returned from validation of the health card? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| f. | If YES, where are they stored? | [5 empty] | <Select> | [25 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
43. |  | Do you capture and store the health card version code, if any? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
44. |  | Is the health number and version code transmitted in result (ORU) messages? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
45. | a. | How do you assign/select patient identifiers (other than the health number) in your LIS?
|  | Patient Identifier |  | Identifier Type |  | Identifier Assigned By |  | Identifier Stored in LIS? | Identifier Ever Reused? | Format |  | Comment
|  | Inpatients | [13 empty] | 0 | 0 |  |  |  | 0 | 0
|  | Outpatients | [13 empty] | 0 | 0 |  |  |  | 0 | 0
|  | Emergency Patients | [13 empty] | 0 | 0 |  |  |  | 0 | 0
|  | Referrals In | [13 empty] | 0 | 0 |  |  |  | 0 | 0
|  | Referrals Out | [13 empty] | 0 | 0 |  |  |  | 0 | 0
|  | Other | [13 empty] | 0 | 0 |  |  |  | 0 | 0
| b. | If a system other than the LIS will be transmitting the results to OLIS, does that system use the same patient identifiers as the LIS? | [6 empty] | <Select> | [24 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
46. |  | For any patient identifiers in your LIS that may be reused, please explain in detail how you establish/ message distinct namespaces for the reused IDs. | [30 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
47. |  | Once a patient identifier is assigned/selected, can demographics associated with patient identifiers be modified in the LIS? | [6 empty] | <Select> | [24 empty] | 0
Put another way, what system is the “source of truth” for patient identifiers and demographics as transmitted in results messages?
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
48. |  | List patient demographics captured in the LIS and describe associated formats, field lengths, and data types. Please provide any specifications documents that you have available.
|  | Demographic Field Name |  | Format |  | Identifier Assigned By |  | Field Length | Data Type | Comments
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
[16 empty] | 0 | 0 |  |  | 0 | [12 empty] | 0
49. | a. | Do you ever move results from one patient in the LIS to another patient? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Describe: | <Enter> | [23 empty] | <Enter>
| b. | Does every such move workflow option cause an HL7 message to be transmitted across the ORU interface? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Describe: | <Enter> | [23 empty] | <Enter>
| c. | Does any data associated with moved test requests/results, other than patient ID and demographics, change as a result of being moved to a different patient (e.g., order IDs, timestamps)? | [9 empty] | <Select> | [23 empty] | 0
|  |  | Describe: | <Enter> | [23 empty] | <Enter>
| d. | If the LIS has system enforced restrictions preventing such moves, does the LIS vendor or any other system or vendor (e.g., HIS) have the capability, if requested, to override such restrictions? | [9 empty] | <Select> | [23 empty] | 0
|  |  | Describe: | <Enter> | [23 empty] | <Enter>
50. | a. | When patient identifiers are merged into the LIS, what happens to clinical lab records/reports for those patient IDs in the LIS? | [29 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
| b. | When patient IDS are merged in the LIS, are any HL7 results messages retransmitted in order to update associated clinical lab records for the subsumed patient ID to the surviving patient ID?
(Include consideration of MRNs, health numbers and other relevant identifiers.)
|  | <Enter> | [34 empty] | <Enter>
51. | a. | What happens to LIS records and reports when patient records must be split (i.e., when data for more than one patient is inadvertently combined under a single patient identifier)?
|  | <Enter> | [34 empty] | <Enter>
| b. | Is this a manual or automated process? | [7 empty] | <Select> | [19 empty] | 0
|  |  | Describe: | <Enter> | [23 empty] | <Enter>
| c. | Are any HL7 messages sent to invalidate previously transmitted lab results and to re-transmit others under a new patient ID? | [7 empty] | <Select> | [24 empty] | 0
|  |  | Describe: | <Enter> | [23 empty] | <Enter>
52. | a. | Does your organization electronically capture and store consent directives or blocking indicators related to disclosure of personal health information? | [7 empty] | <Select> | [24 empty] | 0
| b. | If YES, describe: |  | <Enter> | [23 empty] | <Enter>
| c. | If YES, what system captures this information? Please describe how consent/blocking directives are applied and maintained and to what degree of granularity. | [30 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
| d. | Does the LIS “know” about patient consent/blocking directives in relationship to lab data? | [7 empty] | <Select> | [24 empty] | 0
| e. | If YES, describe: |  | <Enter> | [23 empty] | <Enter>
| f. | If YES, does the existing outbound interface for lab results transmit data elements related to patient consent/ blocking directives? | [7 empty] | <Select> | [24 empty] | 0
| g. | If YES, describe: |  | <Enter> | [23 empty] | <Enter>
Business Processes for Processing Laboratory Information – Current State
53. | a. | From what system will results be transmitted to OLIS (e.g., LIS, HIS/CIS, other – integrated system)? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
| b. | If not LIS, does any other system model results/report data in the same way as the LIS? | [6 empty] | <Select> | [23 empty] | 0
| c. | If YES, describe: |  | <Enter> | [23 empty] | <Enter>
| d. | If NO, do both systems have a common state model? | [6 empty] | <Select>
| e. | Are states applied at the same level of granularity in both systems (e.g., report level vs result level)? | [6 empty] | <Select>
| f. | Are all of the data elements included in the LIS report also reported from the other system? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
54. |  | Does your outbound interface support record-oriented/discrete or display-oriented message formats (or both)? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
55. | a. | Do you currently report preliminary results? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| b. | If YES, which modalities? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
| c. | If YES, are preliminary results sent across the ORU interface? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
56. | a. | Do you send partial reports? | [6 empty] | <Select> | [23 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| b. | If YES, describe what you mean by partial report? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
| c. | If YES, describe how a partial report is communicated as such in an HL7 message (e.g., OBR.25 test request status = “A”; OBX.11 observation result status = “S”; other approach)? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
57. |  | Please identify and document the laboratory providers who have access to historical laboratory results. | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
58. |  | Please identify and document the help desk structure process that supports your organization, including the key contacts. | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
59. |  | Please identify and document the resource(s) who will assume the registration authority for users of each system that will communicate with OLIS from your organization.
|  | System Name |  | Registration Resource
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
Testing – Current State
60. |  | Do you have test environments for each of your (distinct) LIS systems?
|  | Application / System |  | Test Environment Available? (Y/N) |  | Comments
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
61. |  | Who is responsible for the maintenance of your test environments (e.g., vendor, in-house support, service contract with a third party)?
|  | Application / System Test Environment |  | Responsibility |  | Comments
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
62. |  | Does the current LIS test environment have the same LIS release version as the production LIS?
|  | Application / System Test Environment |  | Same version as production? (Y/N) |  | Comments
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
[14 empty] | 0 |  | 0 | 0
63. |  | Describe your most recent data cleansing activities in the production (live) system and test system (e.g., removing duplicates or unnecessary tests).
|  |  | Production system: | <Enter> | [23 empty] | <Enter>
|  |  | Test system: | <Enter> | [23 empty] | <Enter>
Technical Capability Analysis
64. |  | Are there any limitations within your interface application or interface engine with signing messages with the OLIS PKI certificate? | [6 empty] | <Select> | [21 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
65. |  | What tool/method do you use to manage PKI certificates on the server? | [6 empty] | <Select> | [21 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
66. | a. | Does your organization support web access at the workstation level? | [6 empty] | <Select> | [21 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
| b. | If YES, is this access available in the lab? | [6 empty] | <Select> | [21 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
67. |  | What web browser and operating system do you use?
|  | Browser |  | Version |  | Browser |  | Version
|  | Microsoft Internet Explorer |  |  |  | Google Chrome | [9 empty] | 0 | 0
|  | Mozilla Firefox |  |  |  | Other (specify) | [9 empty] | 0 | 0
|  |  | Operating system: | <Enter> | [23 empty] | <Enter>
68. |  | Does your org have a standard desktop configuration (e.g., Windows XP)? | [6 empty] | <Select> | [21 empty] | 0
|  |  | Comments: | <Enter> | [23 empty] | <Enter>
Technical Capability Analysis – Future State
69. |  | What work is required to meet OLIS formal rules as defined in the HL7 specification? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
70. |  | If you have a customized solution, what site specified efforts and/or resources are necessary to interface with OLIS? Please provide documentation/manuals if available. | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
71. |  | What is the approval process and estimated timeline for completion of agreements with eHealth Ontario? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
Project Schedule – Constraints and Dependencies
72. |  | Will you be undertaking any IT and/or lab upgrades during the implementation timelines for this project (e.g., software/hardware upgrades/changes/moves, LIS/HIS/interface engine upgrades)? If YES, provide details below:
|  | Upgrade |  | When |  | Module(s) |  | Version |  | Scope |  | Time to Complete
[16 empty] | 0 | 0 | 0 | 0 |  | 0 | 0
[16 empty] | 0 | 0 | 0 | 0 |  | 0 | 0
[16 empty] | 0 | 0 | 0 | 0 |  | 0 | 0
[16 empty] | 0 | 0 | 0 | 0 |  | 0 | 0
[16 empty] | 0 | 0 | 0 | 0 |  | 0 | 0
73. |  | Do you anticipate that the upgrade(s) and OLIS implementation can be conducted at the same time? | [28 empty] | 0
|  | <Enter> | [34 empty] | <Enter>
74. |  | Are there specific business events, other projects, or currently planned initiatives that will take place prior to, or current with, this project that may impact timelines and resources?
(e.g., a technology upgrade, lab certification, facility infrastructure change)?
|  | Business Event / Other Project / Initiative |  |  | Resource Impact? (Y/N) |  | Timelines Impact? (Y/N) |  | Timelines
[15 empty] | 0 | 0 | 0 | [14 empty] | 0
[15 empty] | 0 | 0 | 0 | [14 empty] | 0
[15 empty] | 0 | 0 | 0 | [14 empty] | 0
[15 empty] | 0 | 0 | 0 | [14 empty] | 0
[15 empty] | 0 | 0 | 0 | [14 empty] | 0
75. |  | Please share any other known risks, constraints, or dependencies which we may encounter during the project that we need to plan for now.
|  | Risks: | <Enter> | [23 empty] | Risks: | <Enter>
|  | Constraints: | <Enter> | [23 empty] | Constraints: | <Enter>
|  | Dependencies: | <Enter> | [23 empty] | Dependencies: | <Enter>
76. |  | Are there any internal processes that would impact the rate at which the project could progress? Consider:
a. Procurement cycles – for engaging consultants; issuing purchase orders for new license agreements
b. Project management policies – decision processes or signoff loops; lead times for acquiring resources
c. System delivery practices – test methodologies/processes; change management policies; lead time for making IT changes; IT change windows/blackout periods
|  | <Enter> | [34 empty] | <Enter>
77. |  | Are there any other policies, standards, or guidelines to which the project would need to align?
|  | <Enter> | [34 empty] | <Enter>
Organization and Team Structure – Resourcing
78. |  | Please specify technical/business expertise (OLIS related) in your organization.
|  | Expertise |  |  | In-House? (Y/N) |  | Contract? (Y/N) |  | Comments
|  | HL7 Developer | [13 empty] | 0 | 0 | [14 empty] | 0
|  | Integration / Developer | [13 empty] | 0 | 0 | [14 empty] | 0
|  | Lab Nomenclature | [13 empty] | 0 | 0 | [14 empty] | 0
|  | Lab Subject Matter Expert | [13 empty] | 0 | 0 | [14 empty] | 0
|  | Tester | [13 empty] | 0 | 0 | [14 empty] | 0
|  | Tester | [13 empty] | 0 | 0 | [14 empty] | 0
|  | Other (specify) | [13 empty] | 0 | 0 | [14 empty] | 0
|  | Other (specify) | [13 empty] | 0 | 0 | [14 empty] | 0
79. |  | Will all sites within your organization work together to resource the OLIS implementation (e.g., share a project manager, work together to complete nomenclature mapping)?
|  | <Enter> | [34 empty] | <Enter>
80. |  | When will you be able to assemble a project team to actively work on this engagement?
|  | <Enter> | [34 empty] | <Enter>

## General
|  |  | Gen Info | Biochemistry | Hematology | Microbiology | Blood Bank | Pathology | Comments
General
1. |  | Identify and document how practitioner demographics are captured and maintained in your system including:
| a. | Which identifiers are used? | <Enter>
| b. | Do you capture and store their regulatory college (e.g., CPSO, CNO, RCDSO) license numbers? | <Select>
| c. | If YES, what is the source for the regulatory license numbers? | <Enter>
| d. | Are identifiers from midwives and nurse practitioners identified or handled differently from other practitioners? | <Select>
| e. | How are changes to practitioner names and numbers made? Is this process different for practitioners other than MDs? | <Enter>
| f. | How many cc’d practitioners do you record within your LIS? | <Enter>
| g. | Do you record internal facility IDs or any other third party IDs in the cc’d fields? | <Select>
| h. | Do you record multiple addresses for a single practitioner in your LIS? | <Select>
| i. | Do you record the practitioner’s first, middle and last names in your LIS? | <Select>
| j. | What do you do if practitioner information is not available in full or part? | <Enter>
| k. | How do you handle out of province practitioners? | <Enter>
2. |  | Does your LIS have/use sort keys?
| a. | For test results? | <Select>
| b. | Are the sort keys sent in messages across the ORU interface? | <Select>
| c. | If no sort keys, is there a reliable business rule governing how requests and results in reports are sequenced? If so, please describe the business rule(s). | <Select>
3. |  | Identify and document business processes used for processing laboratory information (e.g., create order, receive specimen, add test results, query test results) when communicating with OLIS including:
| a. | Communication with external organizations such as public health laboratories and other referral laboratories. | <Enter>
| b. | How tests will be handled and reported (separately from OLIS) that are part of clinical trials, private testing workforce/safety employee tests, or those tests out of scope for OLIS. | <Enter>
| c. | How your organization will choose to identify tests that are not performed. | <Enter>
4. |  | Describe how you receive specimens. | <Enter>
| a. | Is it necessary to order a test in the LIS to enter results? | <Select>
| b. | Which of the following methods do you use to create an order in the LIS? (please select all that apply). | <Select>
5. | a. | Are order/accession numbers ever reused? | <Select>
| b. | Do you have a number “wheel” which is restarted each year? | <Select>
| c. | If YES, how do you establish uniqueness across multiple years? | <Enter>
| d. | Is the order/accession number alpha, numeric or alpha numeric? | <Select>
| e. | What is the maximum number of characters? | <Enter>
6. |  | Do you record date/time stamp at the time of requisition creation, sample sorting, order entry, resulting, and reporting? | <Select>
7. | a. | Can you include multiple test requests in a single order/accession number? | <Select>
| b. | If YES, how many? | <Enter>
| c. | Are your order numbers the same as your accession numbers? | <Select>
| d. | If not, can there be multiple order numbers per accession number (or vice versa)? | <Select>
8. | a. | Does a reflexed test generate a separate order? | <Select>
| b. | Does a reflexed test generate a separate test request? | <Select>
| c. | Is a reflexed test sent as an additional result under an existing test request? | <Select>
9. |  | How do you treat insured and non-insured (private pay) tests ordered on the same requisition? | <Enter>
10. |  | Describe for each of the modalities how you modify an order in the LIS? | <Enter>
11. |  | Describe cancellation scenarios (include all possible workflows):
| a. | How do you cancel an order for a resulted test? | <Enter>
| b. | How do you cancel a single resulted test within an order for multiple tests and for which at least one test has been resulted? | <Enter>
| c. | Does every workflow option for every applicable scenario cause an HL7 message to be transmitted across the OLIS interface? | <Select>
12. |  | Does your outbound ORU interface support:
| a. | Record-oriented/discrete or display-oriented message formats (or both)? | <Select>
| b. | Test codes in OBX.3 or undifferentiated lines of formatted text? | <Select>
13. | a. | Describe how you correct a result in the LIS – include all the possible workflows. (Please provide SOP, if any.) | <Enter>
| b. | Is each (affected) observation corrected separately? | <Select>
| c. | Is it possible to correct a single observation without all of the other observations in the report being designated as corrected? | <Select>
| d. | Is the reason for the correction provided? | <Select>
| e. | If YES, where? | <Enter>
| f. | Is the previously reported result’s date/time included with the explanation? | <Select>
| g. | Does every correction workflow cause an HL7 message to be transmitted across the ORU interface? | <Select>
14. |  | Invalidations as understood by OLIS are distinct from corrections. A correction means that a test result for a given patient has been modified – that is, replaced with a “better” result. Invalidation is used to address a situation where a test result was never applicable for this patient (e.g., a sample was mislabelled), thus there is no replacement result.
| a. | Describe how you invalidate a result in the LIS (include all possible workflows). (Please provide SOP, if any.) | <Enter>
| b. | Is the reason for the invalidation provided? | <Select>
| c. | If YES, where? | <Enter>
| d. | Is the previously reported result’s date/time included with the explanation? | <Select>
| e. | Does every invalidation workflow option cause an HL7 message to be transmitted across the ORU interface? | <Select>
15. |  | Is there any information which is included in your site’s LIS or HIS reports that is not in reports created based on HL7 ORU messages (e.g., system generated comments, ancillary information (clinical information), collector’s comments)? | <Select>
16. | a. | In your LIS do you logically distinguish between reference ranges and other interpretation information, such as interpretation comments, therapeutic range, reference citations, etc.? | <Select>
| b. | Do you send reference ranges in OBX.7 or notes? | <Select>
17. | a. | Does your LIS store a data element or attribute which indicates that an ordered test, for which a sample has been collected, was not performed? Consider both the case where no test has yet been resulted for an order and the case where at least one test has already been resulted for the order. | <Select>
| b. | Do you send a message when a test request, for which a sample has been collected, is not performed? | <Select>
18. | a. | How does your LIS know whether results are designated as reportable to public health, Cancer Care Ontario, etc.? | <Enter>
| b. | Are reportable results captured in the LIS? | <Select>
19. |  | Is the specimen type for each test determined dynamically or set in the test dictionary? | <Select>
20. |  | Is the data type for the result value for each test determined dynamically or set in the test dictionary? | <Select>
Data types: QN (quantitative – numeric result); ST (string text); FT (formatted text); TX (text); DS (date stamp); CE (coded entry – a code, a description and a table reference number); ED (encapsulated data – e.g., PDF, JPG)
21. | a. | For referred in and referred out testing, is the performing (i.e., reference) lab identified distinctly from the reporting (i.e., referring) lab? | <Select> | <Select> | <Select> | <Select> | <Select> | <Select>
| b. | If YES, how? | <Select> | <Select> | <Select> | <Select> | <Select> | <Select>
| c. | Comments:

## Chemistry
Comments
Chemistry
1. | Is your serology done in chemistry, microbiology, or its own separate module? (Related to where related conformance tests will be assessed and which scenarios will need to be repeated or not.) | <Select> | <Enter>

## Hematology
Comments
Hematology
1. | Is an automated differential reported under a CBC or does it have a separate test request code? | <Select> | <Enter>
2. | Where a manual differential is performed after the automated differential, do you also report the auto differential or is it suppressed? | <Select> | <Enter>
3. | If a manual differential is reflexed, based on business rules around the auto differential results, is the manual differential sent under the same accession number? | <Select> | <Enter>
4. | Does it have a unique order ID within the access number? | <Select> | <Enter>
5. | In reports, do you distinguish between auto and manual differential results for the same cell counts? | <Select> | <Enter>
6. | Do you report a PT along with an INR or just the INR? | <Select> | <Enter>

## Microbiology
Comments
Microbiology
1. |  | Please describe how reporting is handled when multiple specimens are included in a single order. | <Enter>
2. |  | Discuss how you report culture results (select). | <Select> | <Enter>
3. |  | How is the parent-child relationship between organisms and antibiotic sensitivities built into the message structure when multiple organisms per specimen are included in a single report? | <Select> | <Enter>
4. |  | Do you report the methods for sensitivities? Please describe. | <Select> | <Enter>
5. |  | How do you report colony counts? | <Select> | <Enter>
6. |  | How are corrections to reports handled? (Please supply SOP if you have one.) Changes to organism which has already been reported:
| a. | Is an HL7 message always sent? | <Select> | <Enter>
| b. | Are any related OBXs also corrected (e.g., coded organism, interpretation, colony count)? | <Select> | <Enter>
| c. | Is sensitivity reported for the previously reported organism also corrected? | <Select> | <Enter>
| d. | If the result status of one observation is corrected, does this affect the status of other results in the same report which have not been corrected? | <Select> | <Enter>
| e. | Is an explanation for the correction sent? | <Select> | <Enter>
| e. | If YES, where? | <Enter>
7. |  | How are invalidations to reports handled? (Please supply SOP if you have one.) To invalidate an organism which has already been reported:
| a. | Is an HL7 message always sent? | <Select> | <Enter>
| b. | Are any related OBXs also corrected (e.g., coded organism, interpretation, colony count)? | <Select> | <Enter>
| c. | Is sensitivity reported for the previously reported organism also corrected? | <Select> | <Enter>
| d. | Is the previously reported result included in the invalidation message? | <Select> | <Enter>
8. |  | How are referrals to public health laboratories (PHL) handled?
| a. | Do you always create an order in the LIS for PHL referrals? | <Select> | <Enter>
| b. | Are results from PHL sent to your lab? | <Select> | <Enter>
| c. | If YES, are results received back from PHL entered into your LIS? | <Select> | <Enter>
| d. | If YES, are these results reported across your ORU interface? | <Select> | <Enter>
| e. | How is PHL as the performing laboratory indicated? | <Select> | <Enter>
9. |  | Is your serology done in chemistry, microbiology, or its own separate module? (Related to where related conformance tests will be assessed and which scenarios will need to be repeated or not.) | <Select> | <Enter>

## Pathology
Comments
Pathology
1. | a. | Has the Cancer Care Ontario (CCO) phase 2 PIMS reporting interface been implemented at your site? | <Select> | <Enter>
| b. | If not, what is the planned implementation schedule? | <Enter>
| c. | Please describe briefly the way the PIMS is captured and transmitted to CCO. | <Enter>
2. | a. | If the CCO phase 2 PIMS reporting interface has not been implemented at your site, do you have an existing ORU interface from your pathology LIS? | <Select> | <Enter>
| b. | If YES, are observations captured / transmitted in separate report sections? | <Select> | <Enter>
| c. | If NOT, is the report sent in a single OBX or one OBX per report line? | <Select> | <Enter>
| d. | If one OBX per report line, what is the maximum number of report lines? | <Enter>
| e. | Do any OBX segments contain patient-identifying information? | <Select> | <Enter>
| f. | “Screen-scrape” of PID segment data? | <Select> | <Enter>
| g. | Details sometimes included in narrative report which could identify a patient? | <Select> | <Enter>
3. |  | How are frozen sections reported (e.g., as preliminary, verbal)? | <Select> | <Enter>
4. |  | Describe whether and how you handle multiple specimens in a single pathology report (e.g., do you use a parent/child mechanism, or is it simply handled via narrative text)? | <Enter>
5. | a. | Do you ever send images with pathology reports? | <Select> | <Enter>
| b. | Please describe file formats supported in your LIS. | <Enter>
| c. | How are addenda to final reports handled in the LIS? | <Enter>
| d. | How are referral consultant reports handled in the LIS? | <Select> | <Enter>
6. | a. | How are corrections to reports handled? (Please supply SOP if you have one.) | <Enter>
| b. | Is each (affected) observation corrected separately? | <Select> | <Enter>
| c. | Is it possible to correct a single observation without all of the other observations in the report being designated as corrected? | <Select> | <Enter>
| d. | Is an explanation supplied providing the reason for the correction? | <Select> | <Enter>
| e. | Is the previously reported result’s date/time supplied with the explanation? | <Select> | <Enter>
7. |  | How are invalidations of reports handled? (Please supply SOP if you have one.) These are what we call “Cancelled” reports where we would transfer to correct patient. Internal comments will move with. | <Enter>
| a. | Is each observation invalidated separately? | <Select> | <Enter>
| b. | Is the original report content preserved in the invalidation message? | <Select> | <Enter>
| c. | Is an explanation supplied providing the reason for the invalidation? | <Select> | <Enter>
| d. | Are any observations deleted? | <Select> | <Enter>
| e. | What result status is applied to invalidated observations? | <Enter>
8. |  | Do you ever send images with genetic test reports? Please describe the formats supported in your LIS. | <Select> | <Enter>
9. |  | Do you report antigen typing results as part of a paternity investigation or family study? | <Select> | <Enter>

## Blood Bank
Comments
Blood Bank
1. |  | Is it necessary to order a test in the LIS to enter results? | <Select> | <Enter>
2. |  | Do you report ABO and Rh as separate results or as one result (e.g., A positive vs A and positive)? | <Select> | <Enter>
3. | a. | Do you report an antibody screen result under the same accession number as the ABO group and Rh type? | <Select> | <Enter>
| b. | Is the antibody screen result reported under the same test request as the group and type, or under a separate test request? | <Select> | <Enter>
4. |  | Do you report antibody investigation results using discrete codes, canned text, or free text? | <Select> | <Enter>
5. | a. | Do you report antibody titres as numeric results against the specific antibodies identified? | <Select> | <Enter>
| b. | If NOT, please describe how you report titres: | <Enter>
6. |  | Do you report direct antiglobulin test results using discrete results or as a free text narrative report? | <Select> | <Enter>
7. | a. | Do you report test results for a cold agglutinin screen as discrete results or as a free text narrative report? | <Select> | <Enter>
| b. | Are titres reported as numeric results, separately from screen results? | <Select> | <Enter>
8. |  | Do you report fetal maternal bleed results as discrete test results or as a free text narrative report? | <Select> | <Enter>
9. |  | Do you report Donath Landsteiner test results as positive/negative or as a free text narrative report? | <Select> | <Enter>
10. |  | Do you report Hams test results as positive/negative or as a free text narrative report? | <Select> | <Enter>
11. |  | Do you report antigen typing results as part of a paternity investigation or family study? | <Select> | <Enter>
12. |  | Do you do investigations for transfusion reactions? | <Select> | <Enter>
| a. | If YES, do you include results of urinalysis, CBC, plasma hemoglobin, icteric index, urine hemosiderin, blood culture, blood product culture, as part of the transfusion reaction investigation? | <Select> | <Enter>
| b. | If YES, do you report discrete test results or a summary of the investigation in narrative format? | <Select> | <Enter>